## Agents
id | agent | stage | reads | writes | must_not | phase1_skill_ids
A1 | Orchestrator | All | Status events from agents; docs/sdlc/kanban.md; checkpoint decisions from humans | Updated kanban.md, gate results, handoff files, checkpoint files, board reports | Change application code; set a checkpoint to APPROVED | A1.01, A1.02, A1.03, A1.04, A1.05, A1.06, A1.12
A2 | Requirements Analyst | Understand | docs/sdlc/inputs/<ID>/ (text, epic, screenshots; Figma link in phase 2) | docs/sdlc/stories/<ID>/ (manifest, stories, acceptance criteria, scope, screen inventory, UX states, UX spec, ready report) | Write kanban.md; invent requirements; mark Ready | A2.01, A2.02, A2.03, A2.04, A2.05, A2.06, A2.07, A2.08, A2.09, A2.10, A2.11
A3 | UI/UX Designer | Plan | Approved stories and UX spec; screenshots or Figma inventory | docs/sdlc/design/<ID>/ (baseline, layout plan, tokens.json, components, responsive rules, checklist); draft theme file | Adopt a theme without CP-02; invent brand values without PROPOSED label | A3.01, A3.02, A3.03, A3.04, A3.05, A3.06, A3.07
A4 | Architect | Plan | Approved stories, scope, NFRs, UX spec, design baseline | docs/sdlc/architecture/ (ADRs, stack analysis, architecture, data model, openapi.yaml, navigation, repo structure, design doc, tasks) | Approve its own ADRs; write application code | A4.01, A4.02, A4.03, A4.04, A4.05, A4.06, A4.07, A4.08, A4.09, A4.10
A5 | Frontend Developer | Build | One task (A4.09), component specs, tokens, layout plan, navigation map, openapi.yaml, mock data | frontend/ source, task plan, task gate result, PR | Change backend/; merge its own PR; skip the task gate | A5.01, A5.02, A5.03, A5.04, A5.05, A5.06
A6 | Backend Engineer | Build | openapi.yaml, data model, one task (A4.09), security review (phase 2) | backend/ source, migrations, seed data, contract validation report, Dockerfile, PR | Change frontend/; merge its own PR; store secret values in files | A6.01, A6.02, A6.03, A6.05, A6.06, A6.07, A6.08
A7 | Test Engineer | Verify | Stories, acceptance criteria, PR branch, openapi.yaml, built screens | docs/sdlc/tests/ (plan, traceability, results, defects, quality summary); test files under tests/, frontend/tests/, backend/tests/ | Change application source beyond test files; record GO or NO-GO | A7.01, A7.02, A7.03, A7.04, A7.05, A7.06, A7.07, A7.08, A7.09
A8 | Reviewer & Release | Verify, Release | PR diff, CI results, ADRs, tokens, quality summary (CP-04 GO) | docs/sdlc/review/ (findings by severity), .github/workflows/, CHANGELOG.md, docs/sdlc/release/ (checklist) | Approve its own release; merge without CP-04 GO; exceed the fix-loop limit without CP-06 | A8.01, A8.02, A8.03, A8.04, A8.05, A8.06, A8.07, A8.08, A8.09, A8.10
S | Shared | All |  |  |  | S.01, S.02, S.03, S.04, S.05, S.06, S.07, S.08, S.09, S.10

## Skills
id | name | owner | used_by | phase | stage | checkpoint | folder | input | steps | output | save_path | verification
A1.01 | Kanban update | A1 | A1 | 1 | All | — | a1-kanban-update | Status event from an agent: item ID, from-column, to-column, evidence file path | 1 Read the event. 2 Check the exit criteria for the current column (stage gate check). 3 If all pass, move the item and add one History row. 4 If a human gate applies, write 'Awaiting approval: <role>' and do not move. 5 Commit: kanban: <ID> <from> → <to> | Updated kanban.md with one new History row | docs/sdlc/kanban.md | Every move has one History row with evidence path
A1.02 | Kanban consistency check | A1 | A1 | 1 | All | — | a1-kanban-consistency-check | docs/sdlc/kanban.md | 1 Check each item appears in one column only. 2 Check every move has a History row. 3 Check each 'Awaiting approval' has a matching checkpoint file | Consistency report listing violations (empty if none) | docs/sdlc/logs/consistency-<date>.md | Report has zero violations or lists each one
A1.03 | Stage gate check | A1 | A1 | 1 | All | CP-01..CP-05 trigger | a1-stage-gate-check | Item ID, current column, exit criteria (from kanban.md Columns table), evidence files | 1 Read the exit criteria for the column. 2 Find evidence for each criterion. 3 Mark each criterion pass or fail with the evidence path. 4 Return the result to A1.01 | Gate result table: criterion, pass/fail, evidence path | docs/sdlc/logs/gate-<ID>-<column>.md | Each criterion has pass/fail and an evidence path
A1.04 | Work item routing | A1 | A1 | 1 | Understand | — | a1-work-item-routing | Item in Backlog or Ready, with its type (story, task, bug) | 1 Read item type. 2 Look up the next agent in the agent table. 3 Write the handoff request | Routing decision: next agent and reason | docs/sdlc/handoffs/<ID>-route.md | Routing matches the agent table in .github/sdlc/config.yml
A1.05 | Checkpoint manager | A1 | A1 | 1 | All | All CP | a1-checkpoint-manager | Any agent request that needs a human decision (decision request or gate) | 1 Create docs/sdlc/checkpoints/CP-xx-<name>.md from the template. 2 Fill: what to decide, options, evidence, default if PROPOSED. 3 Set status OPEN. 4 Block the item in kanban.md. 5 Record the human decision with name and date when given. Never set status APPROVED yourself | Checkpoint file with status OPEN, APPROVED or REJECTED | docs/sdlc/checkpoints/CP-xx-<name>.md | Status is set only by a named human; no agent sets APPROVED
A1.06 | Handoff recorder | A1 | A1 | 1 | All | — | a1-handoff-recorder | Output of a finished agent step and its verification result (S.04) | 1 Check the verification result is PASS. 2 Write the handoff file: from, to, input files, output files, open checkpoints. 3 Add the handoff path to the item in kanban.md | Handoff file linking input and output files | docs/sdlc/handoffs/<ID>-<from>-to-<to>.md | Every output file listed exists at its path
A1.07 | Board status report | A1 | A1 | 2 | All | — | a1-board-status-report | docs/sdlc/kanban.md | 1 Count items per column. 2 List blocked items and items awaiting a checkpoint. 3 Name the bottleneck column | Board status summary | docs/sdlc/logs/board-status-<date>.md | Counts add up to the total items on the board
A1.08 | Flow metrics | A1 | A1 | 3 | All | — | a1-flow-metrics | History table in docs/sdlc/kanban.md | 1 Compute lead time (Backlog to Done). 2 Compute cycle time (In Progress to Done). 3 Compute throughput per week | Flow metrics table | docs/sdlc/logs/metrics-<date>.md | Each metric shows its formula and row count used
A1.09 | Daily standup summary | A1 | A1 | 3 | All | — | a1-daily-standup-summary | docs/sdlc/kanban.md and the last day of handoff files | 1 Group items by done, in progress, blocked. 2 List the agent that holds each item | Standup summary per agent | docs/sdlc/logs/standup-<date>.md | Every item on the board appears once
A1.10 | Retrospective facilitation | A1 | A1 | 3 | All | — | a1-retrospective-facilitation | Flow metrics, blocked items, fix-loop counts from A8.04 | 1 Collect cycle time, blockers, defects. 2 Draft three questions per topic. 3 Leave decisions to the team | Retrospective draft | docs/sdlc/logs/retro-<date>.md | Every point cites a metric or a file
A1.11 | Sprint planning support | A1 | A1 | 3 | Understand | CP-01 | a1-sprint-planning-support | Ready items and capacity (TBD if not given) | 1 List Ready items. 2 Show capacity figures, TBD where not given. 3 Propose two sprint goal options | Sprint options for a human to choose | docs/sdlc/logs/sprint-<date>.md | Every option lists the items it includes
A1.12 | Project bootstrap | A1 | A1 | 1 | All | — | a1-project-bootstrap | .github/sdlc/config.yml (filled by a human) and an empty docs/sdlc/ | 1 Read config.yml and stop if a required value is missing. 2 Create docs/sdlc/ with kanban.md (Columns table from config), inputs/, stories/, design/, architecture/, build/, tests/, review/, release/, checkpoints/, handoffs/, logs/. 3 Write a README in docs/sdlc/ naming the first prompt to run. 4 Commit: sdlc: bootstrap | docs/sdlc/ tree and an empty kanban.md with the Columns table | docs/sdlc/ | Every folder in the Folder Tree sheet exists; kanban.md has 8 columns
A2.01 | Input intake and type detection | A2 | A2 | 1 | Understand | — | a2-input-intake-and-type-detection | Raw input in docs/sdlc/inputs/<ID>/: text story, epic text, screenshot files (PNG/JPG), Figma link (phase 2) | 1 List every input file or link. 2 Assign an ID: T-01 text, SS-01 screenshot, FIG-01 Figma. 3 Detect type: story, epic, screenshot, Figma, mixed. 4 Write the manifest | Input manifest: ID, type, file path, date received | docs/sdlc/stories/<ID>/manifest.md | Every input has an ID, type and file path
A2.02 | Epic decomposition | A2 | A2 | 1 | Understand | — | a2-epic-decomposition | Epic text from the manifest | 1 Read the epic. 2 Split into features by user goal. 3 Give each feature an ID (US-001…). 4 List features that the epic does not state as TBD | Feature list with IDs and source reference | docs/sdlc/stories/<ID>/features.md | Every feature cites a sentence of the epic
A2.03 | User story writing | A2 | A2 | 1 | Understand | — | a2-user-story-writing | Feature list or story text from the manifest | 1 Write each story as: As a <role>, I want <goal>, so that <benefit>. 2 Use only roles and goals in the source. 3 Mark any missing role or benefit TBD | User stories with IDs and source IDs | docs/sdlc/stories/<ID>/stories.md | Every story has role, goal and benefit, or TBD
A2.04 | Acceptance criteria (Given/When/Then) | A2 | A2 | 1 | Understand | — | a2-acceptance-criteria | User stories | 1 For each story write 2-5 Given/When/Then criteria. 2 Each criterion has one observable result. 3 Note platform differences where the source states them. 4 Mark unknown results TBD | Acceptance criteria per story | docs/sdlc/stories/<ID>/acceptance-criteria.md | Each criterion has one observable result; no 'should work well'
A2.05 | Platform and scope definition | A2 | A2 | 1 | Understand | CP-01 | a2-platform-and-scope-definition | Manifest, stories, request text | 1 List target platform: web, mobile, or both. 2 List browsers or OS versions only if the source states them. 3 Write the in-scope and out-of-scope list. 4 Mark gaps TBD | Scope statement with in-scope and out-of-scope lists | docs/sdlc/stories/<ID>/scope.md | Every platform line states its source or TBD
A2.06 | Screenshot screen inventory | A2 | A2 | 1 | Understand | — | a2-screenshot-screen-inventory | Screenshot files (SS-01…) | 1 Open each screenshot. 2 Name each screen and region with an ID (SS-01-R1). 3 List visible text, buttons, inputs and navigation. 4 Mark values read from pixels as estimated | Screen inventory: screen ID, region IDs, visible text, controls | docs/sdlc/stories/<ID>/screen-inventory.md | Every screen has a screenshot region ID; estimates are labelled
A2.07 | UX state definition | A2 | A2 | 1 | Understand | — | a2-ux-state-definition | Screen inventory and stories | 1 For each screen check loading, empty, error, offline, permission-denied. 2 Write the state text the source gives. 3 Mark unknown states TBD and add a checkpoint entry | State matrix: screen × state | docs/sdlc/stories/<ID>/ux-states.md | Every screen has all five states, each stated or TBD
A2.08 | UX spec writing | A2 | A2 | 1 | Understand | CP-01 | a2-ux-spec-writing | Screen inventory, states, stories | 1 Write one section per screen: purpose, controls, flow to next screen. 2 Leave design choices the source does not make as TBD. 3 Cite the source for each line | Screen-level UX spec | docs/sdlc/stories/<ID>/ux-spec.md | No line without a source ID or TBD
A2.09 | Definition of Ready check | A2 | A2 | 1 | Understand | CP-01 | a2-definition-of-ready-check | Stories, criteria, scope, UX spec, checkpoint log (S.02) | 1 Check each story against the Definition of Ready in .github/sdlc/config.yml. 2 Record pass or fail per story with evidence. 3 If all pass, request CP-01 through A1.05. 4 If any fail, return to the author skill | Ready report: story, check, pass/fail, evidence | docs/sdlc/stories/<ID>/ready-report.md | Every story has a pass or fail result with evidence
A2.10 | Clarifying question and checkpoint builder | A2 | A2 | 1 | Understand | CP-07 | a2-clarifying-question-and-checkpoint-builder | Any TBD found by A2 skills | 1 List each TBD with the file and line it appears in. 2 Write the question with 2-3 options. 3 Send each to A1.05 as a checkpoint | Checkpoint requests (CP-07 entries) | docs/sdlc/checkpoints/CP-07-<topic>.md | Every TBD in the stories folder has one checkpoint entry
A2.11 | Scope check against input | A2 | A2 | 1 | Understand | — | a2-scope-check-against-input | Stories and input manifest | 1 Map each story to an input ID. 2 Flag any story without a source. 3 Move suggested extra features to a decision request (S.03), not into scope | Scope check table: story, input ID, status | docs/sdlc/stories/<ID>/scope-check.md | Every story has an input ID or a flag
A2.12 | NFR capture | A2 | A2 | 2 | Understand | — | a2-nfr-capture | Stories and any non-functional requirements in the source | 1 List performance, offline, accessibility, size and battery needs stated in the source. 2 Mark each unstated value TBD | NFR list with TBD values | docs/sdlc/stories/<ID>/nfr.md | Every NFR cites its source or TBD
A2.13 | Privacy and data requirement capture | A2 | A2 | 2 | Understand | CP-09 | a2-privacy-and-data-requirement-capture | Stories | 1 List personal data fields the stories name. 2 List permissions and consent the stories imply. 3 Mark the rest TBD | Privacy requirement list | docs/sdlc/stories/<ID>/privacy.md | Each personal data field cites a story
A2.14 | Figma design read | A2 | A2 | 2 | Understand | CP-08 | a2-figma-design-read | Figma link or file (read access granted at CP-08) | 1 Read frames and components via the Figma connector. 2 Record each screen with its node ID. 3 Record text and component names exactly. 4 Stop and report if access is denied | Figma inventory: screen, node ID, components, text | docs/sdlc/stories/<ID>/figma-inventory.md | Every screen has a Figma node ID
A2.15 | Figma vs story gap check | A2 | A2 | 2 | Understand | — | a2-figma-vs-story-gap-check | Stories and Figma or screenshot inventory | 1 Compare each story with the screens. 2 List screens with no story, and stories with no screen. 3 Cite both IDs | Gap list citing story and screen IDs | docs/sdlc/stories/<ID>/gap-check.md | Each gap cites both IDs
A2.16 | Edge case and glossary extraction | A2 | A2 | 2 | Understand | — | a2-edge-case-and-glossary-extraction | Stories, criteria, input text | 1 List edge cases stated or implied by the source. 2 List domain terms with the source sentence. 3 Log unclear terms | Edge-case list and glossary | docs/sdlc/stories/<ID>/edge-cases-glossary.md | Each term has a source sentence
A3.01 | Text-only UX baseline (PROPOSED) | A3 | A3 | 1 | Plan | CP-02 | a3-text-only-ux-baseline | Approved stories and UX spec (no screenshot or Figma) | 1 Derive user journeys from the stories. 2 List screens and navigation between them. 3 Define screen states. 4 Label everything PROPOSED with a reason | PROPOSED UI/UX baseline | docs/sdlc/design/<ID>/ui-baseline.md | Every screen traces to a story; every item is labelled PROPOSED
A3.02 | Screenshot design extraction | A3 | A3 | 1 | Plan | CP-02 | a3-screenshot-design-extraction | Screen inventory (A2.06) and screenshot files | 1 Read colours, font sizes, spacing and radius from each screenshot. 2 Record each value as estimated. 3 Group values into candidate tokens | Extracted design values, all marked estimated | docs/sdlc/design/<ID>/extracted-design.md | Every value is marked estimated and cites a region ID
A3.03 | Baseline UI layout plan | A3 | A3 | 1 | Plan | CP-02 | a3-baseline-ui-layout-plan | UI baseline or extracted design, screen inventory | 1 For each screen write a text wireframe: regions, primary action, order of content. 2 Confirm one primary action per screen. 3 Label PROPOSED where the source is silent | Layout plan per screen | docs/sdlc/design/<ID>/layout-plan.md | Each screen has exactly one primary action
A3.04 | Design tokens (extracted or PROPOSED) | A3 | A3 | 1 | Plan | CP-02 | a3-design-tokens | Extracted design values (A3.02) or PROPOSED defaults | 1 Set colour, type scale, spacing and radius tokens. 2 Give each token a reason or source. 3 Check text contrast against 4.5:1 with a tool. 4 Save as JSON | tokens.json with reason and source per token | docs/sdlc/design/<ID>/tokens.json | Every text colour pair passes 4.5:1 per the tool output
A3.05 | Component spec writer | A3 | A3 | 1 | Plan | CP-02 | a3-component-spec-writer | Layout plan and tokens | 1 List each component on each screen. 2 For each, write props, states, variants and sizes. 3 Refer to tokens by name only | Component spec list | docs/sdlc/design/<ID>/components.md | Each component lists its states
A3.06 | Responsive layout rules | A3 | A3 | 1 | Plan | CP-02 | a3-responsive-layout-rules | Layout plan and platform scope from A2.05 | 1 Define a rule for each supported width (web) or screen size and orientation (mobile). 2 Define safe areas and text scaling. 3 Mark sizes not in scope TBD | Responsive rule table | docs/sdlc/design/<ID>/responsive.md | Each screen has a rule for each supported size
A3.07 | Design system bootstrap | A3 | A3 | 1 | Plan | CP-02 | a3-design-system-bootstrap | tokens.json and component specs; existing theme file if any | 1 Check for an existing theme file. 2 Draft the theme file from tokens. 3 Mark it NOT ADOPTED. 4 Request CP-02 through A4.10 | Draft theme file, marked NOT ADOPTED | frontend/src/theme/ (draft only until CP-02 approved) | File carries NOT ADOPTED until a named approval is recorded
A3.08 | UX heuristics review | A3 | A3 | 2 | Plan | — | a3-ux-heuristics-review | UI baseline and layout plan | 1 Check visibility of status, error prevention, consistency and feedback. 2 List each violation with the screen ID | Heuristic violation list | docs/sdlc/design/<ID>/heuristics.md | Each violation cites a screen ID
A3.09 | Design source replacement | A3 | A3 | 2 | Plan | CP-02 | a3-design-source-replacement | PROPOSED baseline and a new Figma or screenshot source | 1 Compare each new source screen with the baseline. 2 Replace PROPOSED values with source values. 3 Log every difference | Updated design and a difference log | docs/sdlc/design/<ID>/source-diff.md | Every changed value appears in the difference log
A3.10 | Figma design extraction | A3 | A3 | 2 | Plan | CP-08 | a3-figma-design-extraction | Figma inventory (A2.14) | 1 Read colour, type, spacing and elevation with node IDs. 2 Record each value with its node ID. 3 Build tokens from the values | Design values with node IDs | docs/sdlc/design/<ID>/figma-design.md | Every value cites a node ID
A3.11 | Design system mapping to existing components | A3 | A3 | 2 | Plan | — | a3-design-system-mapping-to-existing-components | Figma components and existing project components | 1 Match each Figma component to a project component. 2 List unmatched items. 3 Log unmatched items as checkpoint entries | Mapping table with matched and unmatched rows | docs/sdlc/design/<ID>/component-map.md | Every Figma component is matched or logged
A3.12 | Asset mapping | A3 | A3 | 2 | Plan | CP-08 | a3-asset-mapping | Figma icons and images | 1 List each icon and image with its node ID. 2 Assign a file name and export density | Asset list with names and densities | docs/sdlc/design/<ID>/assets.md | Every asset has a node ID and a file name
A3.13 | Accessibility annotations extract | A3 | A3 | 2 | Plan | — | a3-accessibility-annotations-extract | Design file or screenshot, component specs | 1 Extract labels, roles, reading order and contrast notes. 2 Mark any value read from pixels as estimated | Accessibility annotation list | docs/sdlc/design/<ID>/a11y-annotations.md | Each annotation cites a screen or node ID
A4.01 | ADR writing | A4 | A4 | 1 | Plan | CP-03 | a4-adr-writing | Decision question and candidate options from the design or stack analysis | 1 Write context. 2 List at least two options with pros and cons. 3 Write the decision as PROPOSED. 4 Add consequences. 5 Leave the status as PROPOSED until a named person approves | ADR-<n> with status PROPOSED | docs/sdlc/architecture/adr/ADR-<n>-<topic>.md | ADR has two or more options and consequences
A4.02 | Stack selection analysis | A4 | A4 | 1 | Plan | CP-03 | a4-stack-selection-analysis | Stories, NFRs, platform scope, team skills (TBD if not given) | 1 List candidate frameworks for web and for mobile (React Native or Flutter if mobile). 2 Compare against needs. 3 Mark missing team data TBD. 4 Write the ADR through A4.01 | Comparison table and ADR draft | docs/sdlc/architecture/stack-analysis.md | Every comparison cell cites a source or TBD
A4.03 | Application architecture design | A4 | A4 | 1 | Plan | CP-03 | a4-application-architecture-design | Approved stack (CP-03), stories, NFRs | 1 Define layers: UI, state, API client, backend services, data. 2 Define module boundaries. 3 Define error and logging approach | Architecture description with a layer diagram in text | docs/sdlc/architecture/architecture.md | Each module has one owner
A4.04 | Data model design | A4 | A4 | 1 | Plan | CP-03 | a4-data-model-design | Stories and acceptance criteria | 1 List entities named in stories. 2 List fields, types and keys only where stated. 3 Mark other fields TBD. 4 Map entity relationships | Entity list with fields, keys and relationships | docs/sdlc/architecture/data-model.md | Every entity cites a story or is marked TBD
A4.05 | API contract design (OpenAPI) | A4 | A4 | 1 | Plan | CP-03 | a4-api-contract-design | Data model, user flows from the UX spec | 1 List endpoints required by each flow. 2 Write request and response schemas. 3 Define error responses. 4 Save as OpenAPI 3 | openapi.yaml | docs/sdlc/architecture/api/openapi.yaml | Contract passes the linter (A6.06)
A4.06 | Navigation and flow design | A4 | A4 | 1 | Plan | CP-02 | a4-navigation-and-flow-design | Screen inventory and UX spec | 1 Map each screen to a stack, tab or modal (mobile) or route (web). 2 Define entry and exit points. 3 List deep links only if the source states them | Navigation map | docs/sdlc/architecture/navigation.md | Every screen appears once in the map
A4.07 | Repository structure plan | A4 | A4 | 1 | Plan | CP-03 | a4-repository-structure-plan | Architecture and stack | 1 Propose folders for frontend, backend, tests, deploy. 2 Check against the team template if one is set in config. 3 Mark missing template TBD | Folder plan | docs/sdlc/architecture/repo-structure.md | Template check passes, or TBD is logged
A4.08 | Design doc writer | A4 | A4 | 1 | Plan | CP-02, CP-03 | a4-design-doc-writer | ADRs, navigation, API contract, data model, UI baseline | 1 Collect the approved parts. 2 Write one design doc with a section per part. 3 Add a section of TBD items | Design document | docs/sdlc/architecture/design-doc-<ID>.md | Every section cites its source file
A4.09 | Task breakdown | A4 | A4 | 1 | Plan | CP-03 | a4-task-breakdown | Approved design doc | 1 Split the design into tasks sized for one PR. 2 Give each task a frontend, backend or test scope. 3 Link each task to its story ID | Task list with story links | docs/sdlc/architecture/tasks-<ID>.md | Every story maps to at least one task
A4.10 | Design approval request | A4 | A4 | 1 | Plan | CP-02, CP-03 | a4-design-approval-request | Design doc and UI baseline | 1 Write the approval request: what to approve, evidence paths, open TBDs. 2 Send to A1.05. 3 Stop until the named approver answers | Approval request for CP-02 or CP-03 | docs/sdlc/checkpoints/CP-02-design.md | Request lists every file the approver must read
A4.11 | Security architecture review | A4 | A4 | 2 | Plan | CP-09 | a4-security-architecture-review | Architecture and data model | 1 Check where secrets are stored. 2 Check transport security and auth flows. 3 List each risk with the file it affects | Security architecture findings | docs/sdlc/architecture/security-review.md | Each finding cites a file
A4.12 | Performance budget definition | A4 | A4 | 2 | Plan | CP-03 | a4-performance-budget-definition | NFRs and platform scope | 1 Propose startup, response-time and bundle-size targets as PROPOSED. 2 Give a reason for each. 3 Leave confirmation to a human | PROPOSED performance budget | docs/sdlc/architecture/performance-budget.md | Every value is PROPOSED with a reason
A4.13 | Third-party dependency evaluation | A4 | A4 | 2 | Plan | — | a4-third-party-dependency-evaluation | Candidate libraries from the ADR | 1 Check maintenance activity, licence, size and known vulnerabilities for each library. 2 Record the source of each fact | Dependency evaluation table | docs/sdlc/architecture/dependency-eval.md | Each fact cites a source
A4.14 | Offline and sync design | A4 | A4 | 3 | Plan | CP-03 | a4-offline-and-sync-design | Offline requirement and data model | 1 Define local storage and cache rules. 2 Define conflict resolution. 3 Mark anything not stated TBD | Offline and sync design | docs/sdlc/architecture/offline-sync.md | Every rule cites a requirement or TBD
A4.15 | Native boundary decision (mobile) | A4 | A4 | 3 | Plan | CP-03 | a4-native-boundary-decision | Architecture and platform needs | 1 List features that need native code. 2 Give trade-offs for each. 3 Request a human decision | Native boundary options | docs/sdlc/architecture/native-boundary.md | Each option lists a trade-off
A5.01 | Task plan | A5 | A5 | 1 | Build | — | a5-task-plan | One task from A4.09 with its story and design files | 1 List files to create or change. 2 List tests to write. 3 List risks. 4 Save the plan before coding | Task plan | docs/sdlc/build/plans/<task-ID>.md | Plan lists every file the PR changes
A5.02 | Component codegen from spec | A5 | A5 | 1 | Build | — | a5-component-codegen-from-spec | Component spec (A3.05) and tokens.json (A3.04) | 1 Create each component from its spec. 2 Use tokens by name only. 3 Implement every listed state | Component source files | frontend/src/components/<Name>/ | No colour, size or spacing value is hard-coded outside tokens
A5.03 | Screen implementation | A5 | A5 | 1 | Build | — | a5-screen-implementation | Layout plan, navigation map, UX spec and states | 1 Build each screen from its layout plan. 2 Implement loading, empty, error and permission-denied states. 3 Use the navigation map for routes | Screen source files | frontend/src/screens/<Name>/ | Each screen implements every state from A2.07
A5.04 | State and navigation management | A5 | A5 | 1 | Build | — | a5-state-and-navigation-management | Architecture ADR for state and routing | 1 Apply the chosen state pattern from the ADR. 2 Apply the chosen routing pattern. 3 Do not mix patterns | State and routing modules | frontend/src/state/, frontend/src/routes/ | Lint rule set from config shows no mixed pattern
A5.05 | API wiring | A5 | A5 | 1 | Build | — | a5-api-wiring | OpenAPI contract (A4.05) and mock data (A6.05) | 1 Call only endpoints in the contract. 2 Map each response to the UI state. 3 Map each error to the error state. 4 Add no behaviour beyond the story | API client and wired screens | frontend/src/api/ | Every call matches an operation in openapi.yaml
A5.06 | Frontend build configuration | A5 | A5 | 1 | Build | — | a5-frontend-build-configuration | Stack from the ADR, environment variable list | 1 Set build tool settings for the stack. 2 Add env variable names with no values. 3 Run the build | Build config and build log | frontend/ (build config files) | Build succeeds on a clean checkout
A5.07 | Accessibility implementation | A5 | A5 | 2 | Build | — | a5-accessibility-implementation | Accessibility annotations (A3.13) and minimum UI/UX checklist (S.10) | 1 Add labels and roles to every control. 2 Add focus order. 3 Check contrast uses tokens. 4 Support text scaling | Accessible components and screens | frontend/src/ | Checklist S.10 items pass for each built screen
A5.08 | Platform-specific code handling | A5 | A5 | 2 | Build | CP-03 | a5-platform-specific-code-handling | Platform scope and stack | 1 Handle browser differences or iOS and Android differences. 2 Isolate platform code in one module per platform. 3 Record each difference | Platform modules and a difference list | frontend/src/platform/ | Every platform branch has a test
A5.09 | Dev log writer | A5 | A5 | 2 | Build | — | a5-dev-log-writer | Changes in the PR and open TBDs | 1 Write what changed and why. 2 List TBDs touched. 3 Link the task ID | Dev log | docs/sdlc/build/devlogs/<task-ID>.md | Dev log lists every changed file
A5.10 | Refactoring and tech debt fixes | A5 | A5 | 3 | Build | — | a5-refactoring-and-tech-debt-fixes | Tech debt list from the retro or the board | 1 Pick one item in scope. 2 Change structure only. 3 Run the existing tests | Refactored code with unchanged behaviour | frontend/src/ | Tests pass before and after the change
A5.11 | Localization and error text | A5 | A5 | 3 | Build | — | a5-localization-and-error-text | Strings used in the UI and the source of translations (TBD if not given) | 1 Move strings to a resource file. 2 Add keys. 3 Leave translations TBD if not given | Resource files with keys | frontend/src/i18n/ | Every UI string uses a key
A6.01 | Data model and migrations | A6 | A6 | 1 | Build | CP-03 | a6-data-model-and-migrations | Data model (A4.04) | 1 Write a migration per entity. 2 Add keys and constraints from the data model. 3 Run the migration on an empty database | Migration files | backend/migrations/ | Migration runs on an empty database with no error
A6.02 | API endpoint implementation | A6 | A6 | 1 | Build | — | a6-api-endpoint-implementation | OpenAPI contract (A4.05) and data model | 1 Implement each operation in the contract. 2 Validate input. 3 Return the contract error shape | Endpoint handlers | backend/src/api/ | Each handler matches its contract operation
A6.03 | Validation and error responses | A6 | A6 | 1 | Build | — | a6-validation-and-error-responses | Contract error schema and validation rules from stories | 1 Validate each field against the story rule. 2 Return the contract error for each failure. 3 Log no personal data | Validation layer | backend/src/validation/ | Each rule has a test that fails on bad input
A6.04 | Auth and authorization | A6 | A6 | 2 | Build | CP-09 | a6-auth-and-authorization | Stories that require sign-in and the security review (A4.11) | 1 Implement only the auth flows the stories name. 2 Store secrets outside code. 3 Check permissions on every protected route | Auth module | backend/src/auth/ | Every protected route has a test for denied access
A6.05 | Mock data generation | A6 | A6 | 1 | Build | — | a6-mock-data-generation | Data model and API contract | 1 Generate rows that match the model. 2 Label every row SYNTHETIC. 3 Use no real personal data | Synthetic seed data | backend/seed/synthetic/ | Every seed file has a SYNTHETIC label
A6.06 | API contract validator | A6 | A6 | 1 | Verify | — | a6-api-contract-validator | openapi.yaml and running backend responses | 1 Run the OpenAPI linter on the contract. 2 Call each endpoint with a test request. 3 Compare each response with its schema | Contract validation report | docs/sdlc/tests/contract-<run>.md | Linter and response checks both pass
A6.07 | Backend environment config and seed | A6 | A6 | 1 | Build | — | a6-backend-environment-config-and-seed | Environment variable names and seed data | 1 List variable names with no values. 2 Add a template env file with placeholders. 3 Add a seed script for synthetic data | Config template and seed script | backend/config/ | Template holds no real values; seed script runs
A6.08 | Backend container and deploy config | A6 | A6 | 1 | Release | — | a6-backend-container-and-deploy-config | Backend build and env variable names | 1 Write a Dockerfile for the backend. 2 Write deploy config with secret references only. 3 Build the image locally | Dockerfile and deploy config | deploy/backend/ | Image builds; no secret value appears in any file
A6.09 | BFF layer design | A6 | A6 | 2 | Plan | CP-03 | a6-bff-layer-design | API contract and UI flows | 1 Map each screen's data needs to one BFF endpoint. 2 Define the response shape per screen. 3 List backend calls per endpoint | BFF specification | docs/sdlc/architecture/bff-spec.md | Every screen maps to one BFF endpoint
A6.10 | BFF implementation | A6 | A6 | 2 | Build | — | a6-bff-implementation | BFF specification | 1 Implement each BFF endpoint from the spec. 2 Call backend services. 3 Map errors to the screen error shape | BFF source | backend/src/bff/ | Each BFF endpoint has a contract test
A6.11 | External service integration | A6 | A6 | 2 | Build | CP-03 | a6-external-service-integration | External service names and contracts from the ADR | 1 Write a client per service. 2 Set timeouts and retries as PROPOSED. 3 Map service errors | Service clients | backend/src/integrations/ | Each client has a test with a fake service
A7.01 | Test plan creation | A7 | A7 | 1 | Verify | — | a7-test-plan-creation | Stories, acceptance criteria, risks, environments | 1 List the scope from stories. 2 List test types per story. 3 List environments and data. 4 List risks | Test plan | docs/sdlc/tests/test-plan-<ID>.md | Every acceptance criterion is in scope
A7.02 | Unit test writing | A7 | A7 | 1 | Verify | — | a7-unit-test-writing | Source files from the PR | 1 Write a test for each branch and state. 2 Use the test runner in config. 3 Run the tests | Unit test files | frontend/tests/unit/, backend/tests/unit/ | Tests pass in the task gate (S.07)
A7.03 | Component testing | A7 | A7 | 1 | Verify | — | a7-component-testing | Component specs and source | 1 Render each component alone. 2 Test each listed state. 3 Test each label and role | Component test files | frontend/tests/components/ | Each state has a test
A7.04 | Integration testing | A7 | A7 | 1 | Verify | — | a7-integration-testing | API contract, data model, running backend | 1 Test each endpoint with real storage in a test database. 2 Test error paths. 3 Test the wiring from API client to screen | Integration test files | backend/tests/integration/ | Each operation has a passing test and each error has one
A7.05 | End-to-end test scripting (web) | A7 | A7 | 1 | Verify | — | a7-end-to-end-test-scripting | User flows from the UX spec and navigation map | 1 Script each flow from the story. 2 Use a real browser. 3 Assert the visible result from the acceptance criterion | E2E test scripts | tests/e2e/ | Every acceptance criterion with a flow has a passing E2E test
A7.06 | Requirement-to-test traceability | A7 | A7 | 1 | Verify | — | a7-requirement-to-test-traceability | Acceptance criteria and tests | 1 Map each criterion to test IDs. 2 Flag criteria with no test. 3 Record the map | Traceability matrix | docs/sdlc/tests/traceability-<ID>.md | Zero criteria without a test or a flag
A7.07 | Defect report writing | A7 | A7 | 1 | Verify | — | a7-defect-report-writing | A failed test with its log | 1 Write steps to reproduce. 2 Record environment, logs and severity. 3 Send to A1.05 as a BUG item | Defect report | docs/sdlc/tests/defects/BUG-<n>.md | Steps reproduce the failure
A7.08 | Test results writer | A7 | A7 | 1 | Verify | — | a7-test-results-writer | Test runner output | 1 Count passed, failed, skipped. 2 Link each failure to a defect. 3 Write the report | Test results report | docs/sdlc/tests/results-<run>.md | Totals match the runner output
A7.09 | Quality gate summary | A7 | A7 | 1 | Verify | CP-04 | a7-quality-gate-summary | Test plan, traceability, results, coverage, defects | 1 Summarise results, coverage, open defects. 2 List open risks. 3 Request CP-04 GO or NO-GO from the named approver. 4 Do not record the decision | Quality summary and CP-04 request | docs/sdlc/tests/quality-summary-<ID>.md | Summary cites each figure to its file
A7.10 | Coverage analysis | A7 | A7 | 2 | Verify | — | a7-coverage-analysis | Coverage report from the test runner | 1 Read line and branch coverage. 2 List untested critical paths. 3 Compare with the threshold in config | Coverage analysis | docs/sdlc/tests/coverage-<run>.md | Each critical path is listed as tested or not
A7.11 | Accessibility testing | A7 | A7 | 2 | Verify | — | a7-accessibility-testing | Built screens and accessibility checklist | 1 Check screen reader labels. 2 Check focus order. 3 Check contrast and target size | Accessibility test report | docs/sdlc/tests/a11y-<run>.md | Each check states pass or fail with a screen ID
A7.12 | Test execution and flaky-test handling | A7 | A7 | 2 | Verify | — | a7-test-execution-and-flaky-test-handling | Repeated test runs | 1 Run the suite several times. 2 Mark a test flaky if results differ. 3 Quarantine it with a defect | Stability report | docs/sdlc/tests/stability-<run>.md | Quarantined tests each have a defect ID
A7.13 | Regression suite maintenance | A7 | A7 | 2 | Verify | — | a7-regression-suite-maintenance | Code changes and failing tests after the change | 1 List tests the change affects. 2 Update them. 3 Remove none without a note | Updated tests and change note | tests/ | Suite passes after update
A7.14 | Device and browser matrix planning | A7 | A7 | 2 | Verify | — | a7-device-and-browser-matrix-planning | Platform scope from A2.05 | 1 List browsers or devices in scope. 2 Give the test order. 3 Mark unlisted devices TBD | Test matrix | docs/sdlc/tests/matrix.md | Every in-scope item has a row
A7.15 | Performance testing | A7 | A7 | 3 | Verify | CP-03 | a7-performance-testing | Performance budget (A4.12) | 1 Measure each budgeted metric. 2 Compare with the budget. 3 Report each result | Performance report | docs/sdlc/tests/perf-<run>.md | Each budget has a measured value
A7.16 | Visual regression | A7 | A7 | 3 | Verify | — | a7-visual-regression | Approved screenshots | 1 Take a screenshot of each screen. 2 Compare with the approved baseline. 3 Send each diff to a human | Diff report | tests/visual/ | Each diff is listed for human review
A8.01 | PR code review | A8 | A8 | 1 | Verify | — | a8-pr-code-review | PR diff, conventions, ADRs | 1 Read the diff. 2 Check logic, naming and convention rules. 3 Write each comment with its file and line | Review comments | docs/sdlc/review/<PR>-review.md | Every comment cites a file and line
A8.02 | Review summary with severity | A8 | A8 | 1 | Verify | — | a8-review-summary-with-severity | Review comments | 1 Group each finding as blocker, major, minor or nit. 2 Write the summary count | Severity summary | docs/sdlc/review/<PR>-summary.md | Every finding has a severity
A8.03 | Review checklist enforcement | A8 | A8 | 1 | Verify | — | a8-review-checklist-enforcement | PR checklist and review checklist from config | 1 Check each checklist item. 2 Mark present or missing. 3 Block the PR if a required item is missing | Checklist result | docs/sdlc/review/<PR>-checklist.md | Every item is marked present or missing
A8.04 | Defect fix loop | A8 | A8 | 1 | Verify | CP-06 | a8-defect-fix-loop | Findings and the developer's fix | 1 Send findings to the developer. 2 Re-review the fix. 3 Count each loop. 4 At the limit in config, request CP-06 from a human | Loop record with count | docs/sdlc/review/<PR>-loops.md | Loop count never exceeds the config limit
A8.05 | Secrets and credential scan | A8 | A8 | 1 | Verify | — | a8-secrets-and-credential-scan | Diff, config files, logs | 1 Run the secret scanner on the diff and config. 2 List each hit by file and line. 3 Block the PR on any hit | Scan report | docs/sdlc/review/<PR>-secrets.md | Scanner output is attached; zero hits or blocked
A8.06 | UI and design standards review | A8 | A8 | 1 | Verify | — | a8-ui-and-design-standards-review | Code, tokens.json, component specs | 1 Check colours and sizes come from tokens. 2 Check each component follows its spec. 3 List each deviation | Deviation list | docs/sdlc/review/<PR>-design.md | Every deviation cites a file and a spec line
A8.07 | CI pipeline configuration | A8 | A8 | 1 | Release | — | a8-ci-pipeline-configuration | Repo build and test commands | 1 Write a workflow for lint, test and build on each PR. 2 Use secrets references only. 3 Run it on a test PR | CI workflow file | .github/workflows/ci.yml | Workflow passes on the test PR
A8.08 | Build and deploy automation | A8 | A8 | 1 | Release | — | a8-build-and-deploy-automation | Build config, deploy config, environment names | 1 Write the build step. 2 Write the deploy step with secret references. 3 Run a dry-run deploy | Deploy workflow file | .github/workflows/deploy.yml | Dry-run deploy passes
A8.09 | Versioning and changelog | A8 | A8 | 1 | Release | — | a8-versioning-and-changelog | Merged PRs since the last release | 1 Choose the version bump from change types. 2 Write changelog entries from PR titles. 3 Link each entry to its PR | CHANGELOG entry | CHANGELOG.md | Every entry links to a PR
A8.10 | Release checklist | A8 | A8 | 1 | Release | CP-05 | a8-release-checklist | Quality summary (CP-04 GO), security results, changelog, deploy config | 1 Check each item: tests green, CP-04 GO recorded, secrets scan clean, config reviewed, rollback plan written. 2 Mark evidence per item. 3 Request CP-05 from the named approver | Release checklist and CP-05 request | docs/sdlc/release/checklist-<version>.md | Every item has evidence; the agent does not approve
A8.11 | Review consolidation | A8 | A8 | 2 | Verify | — | a8-review-consolidation | Outputs of several reviews | 1 Merge findings. 2 Remove duplicates. 3 Keep the highest severity | Consolidated findings | docs/sdlc/review/<PR>-consolidated.md | No duplicate finding remains
A8.12 | Security review (OWASP ASVS / MASVS) | A8 | A8 | 2 | Verify | CP-09 | a8-security-review | Code, auth design, data model | 1 Check input handling, storage, auth and transport against ASVS (web) or MASVS (mobile). 2 List each finding with the file | Security findings | docs/sdlc/review/<PR>-security.md | Each finding cites an ASVS or MASVS item
A8.13 | Dependency vulnerability check | A8 | A8 | 2 | Verify | — | a8-dependency-vulnerability-check | Dependency manifests and lock files | 1 Run the dependency audit tool. 2 List each advisory and licence issue | Audit report | docs/sdlc/review/<PR>-deps.md | Tool output is attached
A8.14 | Privacy and PII in logs review | A8 | A8 | 2 | Verify | CP-09 | a8-privacy-and-pii-in-logs-review | Logging code and analytics calls | 1 Find each log or analytics call with personal fields. 2 List each with its file and line | PII findings | docs/sdlc/review/<PR>-pii.md | Each finding cites a file and line
A8.15 | Architecture conformance review | A8 | A8 | 2 | Verify | — | a8-architecture-conformance-review | Code, ADRs, design doc | 1 Compare module layout with the architecture doc. 2 List each deviation | Conformance findings | docs/sdlc/review/<PR>-architecture.md | Each deviation cites an ADR section
A8.16 | Accessibility review | A8 | A8 | 2 | Verify | — | a8-accessibility-review | Built code and screens | 1 Check labels, focus order, contrast and target size in code. 2 List each finding | Accessibility findings | docs/sdlc/review/<PR>-a11y.md | Each finding cites a file
A8.17 | Crash and release monitoring setup | A8 | A8 | 2 | Release | — | a8-crash-and-release-monitoring-setup | Release target and monitoring tool choice (TBD if not set) | 1 Add the crash reporter config. 2 Add env variable names only. 3 Test one crash event in staging | Monitoring config | deploy/monitoring/ | One test event appears in the tool
A8.18 | Staged rollout and rollback plan | A8 | A8 | 3 | Release | CP-05 | a8-staged-rollout-and-rollback-plan | Release checklist and deploy config | 1 Set rollout percentages as PROPOSED. 2 Write rollback steps. 3 Request CP-05 with the plan | Rollout and rollback plan | docs/sdlc/release/rollout-<version>.md | Every step names an owner
A8.19 | Store submission preparation (mobile) | A8 | A8 | 3 | Release | CP-05 | a8-store-submission-preparation | Store metadata and screenshots | 1 Prepare metadata and review notes. 2 Check privacy labels. 3 Leave the submission for a human | Submission package | docs/sdlc/release/store/ | Package lists each required field
A8.20 | Code signing and secrets management (mobile) | A8 | A8 | 3 | Release | — | a8-code-signing-and-secrets-management | Certificate and key requirements | 1 List needed signing items. 2 Store them as CI secrets. 3 Write no key to the repo | Signing setup notes | docs/sdlc/release/signing.md | No key file appears in the repo
A8.21 | OTA update configuration (mobile) | A8 | A8 | 3 | Release | CP-05 | a8-ota-update-configuration | Release rules for OTA | 1 Write the rule for what may ship OTA. 2 Write the config with secret references | OTA config and rule | deploy/ota/ | Rule lists each allowed change type
A8.22 | Dependency update automation | A8 | A8 | 3 | Release | — | a8-dependency-update-automation | Dependency manifests | 1 Write the update bot config. 2 Set the schedule as PROPOSED | Update bot config | .github/dependabot.yml | Config validates
A8.23 | Performance review | A8 | A8 | 3 | Verify | — | a8-performance-review | Code and performance budget | 1 Find re-renders, unvirtualised lists and blocking work. 2 List each with its file | Performance findings | docs/sdlc/review/<PR>-perf.md | Each finding cites a file
S.01 | Source traceability check | Shared | All | 1 | All | — | shared-source-traceability-check | Any output file and its source IDs | 1 Check each item cites an input ID, file or line. 2 Flag each item with no source as TBD | Traceability report | docs/sdlc/logs/traceability-<file>.md | Zero untraced items, or each is flagged
S.02 | Assumption and checkpoint log | Shared | All | 1 | All | All CP | shared-assumption-and-checkpoint-log | Any gap in a source file | 1 Record the gap with the file and line. 2 List two or more options. 3 Send to A1.05 as a checkpoint. 4 Never choose a default | Log entry and checkpoint request | docs/sdlc/checkpoints/ (via A1.05) | Each entry has two or more options or says TBD
S.03 | Decision request (human) | Shared | All | 1 | All | All CP | shared-decision-request | Options with trade-offs | 1 Write each option with its trade-off. 2 Give the PROPOSED default and reason. 3 Stop until a named person decides | Decision request in a checkpoint file | docs/sdlc/checkpoints/CP-xx-<name>.md | Request names who decides and what file they read
S.04 | Independent output verification | Shared | All | 1 | All | — | shared-independent-output-verification | An output file and the input it used | 1 Open a new chat with no prior context. 2 Compare the output with the input. 3 Mark each item PASS or FAIL with the reason. 4 Do not fix anything | Verification record: item, PASS/FAIL, reason | docs/sdlc/logs/verify-<file>.md | Every item has PASS or FAIL
S.05 | Documentation writing (templates) | Shared | A2,A4,A7,A8 | 1 | All | — | shared-documentation-writing | Template from .github/sdlc/templates/ and sources | 1 Pick the template. 2 Fill each field from a source. 3 Write TBD for each gap. 4 Do not add fields the template lacks | Filled document | as set by the calling skill | Every field has a source or TBD
S.06 | Git operations | Shared | A1,A5,A6,A8 | 1 | All | — | shared-git-operations | Branch, commit or PR request | 1 Create the branch named <type>/<task-ID>. 2 Commit with a conventional message. 3 Open the PR. 4 Read CI status. Only A1 commits docs/sdlc/kanban.md | Branch, commit, PR link, CI status | git (no file) | CI status is recorded in the handoff file
S.07 | Task gate (lint, types, unit tests) and commit | Shared | A5,A6 | 1 | Build | — | shared-task-gate-and-commit | Code changes for one task | 1 Run lint. 2 Run the type check. 3 Run the unit tests. 4 Commit only if all three pass | Task gate result file | docs/sdlc/build/task-gate-<task-ID>.md | All three results are recorded as pass
S.08 | Pull request creation | Shared | A5,A6 | 1 | Build | — | shared-pull-request-creation | Commits, task ID, test results | 1 Write the summary, test notes and linked task ID. 2 Attach the task gate result. 3 Open the PR | PR description | docs/sdlc/build/pr-<task-ID>.md | CI is green before review starts
S.09 | Bug fixing | Shared | A5,A6 | 1 | Build | — | shared-bug-fixing | Defect report (A7.07) | 1 Reproduce the failure. 2 Find the root cause. 3 Apply a minimal fix. 4 Add a test that fails before and passes after | Fix commit and test | source files as changed | The new test fails before the fix and passes after
S.10 | Minimum UI/UX checklist | Shared | A3,A5,A8 | 1 | Plan | — | shared-minimum-ui-ux-checklist | UI baseline or built screens | 1 Check one primary action per screen. 2 Check loading, empty, error, offline and permission states. 3 Check labels, touch targets (44 pt iOS, 48 dp Android, 24 CSS px web), contrast 4.5:1, text scaling, feedback. 4 Record pass or fail per item | Checklist result per screen | docs/sdlc/design/<ID>/ui-checklist.md | Every item has pass or fail with evidence
S.11 | Secure coding baseline | Shared | A5,A6 | 2 | Build | — | shared-secure-coding-baseline | Source files in the PR | 1 Check for hard-coded secrets. 2 Check input is validated and output is escaped. 3 Check storage and transport use approved methods | Secure coding findings | docs/sdlc/review/<PR>-secure-coding.md | Each finding cites a file and line
S.12 | Compliance checklist | Shared | A4,A8 | 2 | Verify | CP-09 | shared-compliance-checklist | Standard to check: OWASP ASVS/MASVS, GDPR/CCPA, store policy | 1 Load the chosen standard. 2 Check each item. 3 Mark pass, fail or not applicable with reason | Compliance checklist | docs/sdlc/review/<ID>-compliance.md | Each item has a result and a reason
S.13 | Estimation | Shared | A1,A2 | 3 | Understand | — | shared-estimation | Story and any team capacity figures (TBD if none) | 1 Size each story against the team's agreed scale in config. 2 Mark TBD where no scale exists | Estimate per story | docs/sdlc/stories/<ID>/estimates.md | Each estimate cites the scale used or TBD

## Plan
section | item | detail
checkpoint | CP-01 Ready | who: Product Owner ¦ raised: After A2.09 Definition of Ready check passes ¦ decides: Stories, acceptance criteria and scope are correct and complete enough to design from ¦ evidence: docs/sdlc/stories/<ID>/ready-report.md and the files it lists ¦ if unanswered: Item stays in Backlog
checkpoint | CP-02 Design approval | who: Product Owner (plus a designer if one exists) ¦ raised: After A4.10 sends the request with the UI baseline or extracted design ¦ decides: UI/UX baseline or extracted design, tokens, layout plan, navigation map; adoption of the theme file ¦ evidence: docs/sdlc/design/<ID>/ and docs/sdlc/architecture/navigation.md ¦ if unanswered: Design stays PROPOSED; no code uses it
checkpoint | CP-03 Architecture approval | who: Tech Lead (or Product Owner if none) ¦ raised: After A4.08 design doc and A4.09 tasks are written ¦ decides: Stack ADR, architecture, data model, API contract, repo structure, task breakdown ¦ evidence: docs/sdlc/architecture/design-doc-<ID>.md and ADRs ¦ if unanswered: No build task starts
checkpoint | CP-04 Quality GO / NO-GO | who: QA Lead (or Product Owner if none) ¦ raised: After A7.09 quality summary ¦ decides: Whether test results, traceability and open defects allow release preparation ¦ evidence: docs/sdlc/tests/quality-summary-<ID>.md ¦ if unanswered: Item stays in Testing
checkpoint | CP-05 Release approval | who: Product Owner ¦ raised: After A8.10 release checklist is complete ¦ decides: Whether the version ships, and the rollout plan ¦ evidence: docs/sdlc/release/checklist-<version>.md ¦ if unanswered: Nothing ships
checkpoint | CP-06 Fix-loop limit reached | who: Tech Lead ¦ raised: When A8.04 loop count reaches the limit in config (PROPOSED 3) ¦ decides: Continue fixing, accept with a note, or send the item back to Design ¦ evidence: docs/sdlc/review/<PR>-loops.md ¦ if unanswered: PR stays blocked
checkpoint | CP-07 Missing requirement / TBD | who: Product Owner ¦ raised: When any skill finds a gap in the source and logs a TBD ¦ decides: The missing value, chosen from the options listed ¦ evidence: docs/sdlc/checkpoints/CP-07-<topic>.md ¦ if unanswered: Value stays TBD; dependent items stay blocked
checkpoint | CP-08 Figma access (phase 2) | who: Repo owner ¦ raised: Before A2.14 reads a Figma file ¦ decides: Grant read access to the file; confirm the file is the source of truth ¦ evidence: Figma link in the manifest ¦ if unanswered: Figma skills do not run; screenshot path is used
checkpoint | CP-09 Security and privacy sign-off (phase 2) | who: Security owner (or Tech Lead) ¦ raised: After A8.12 and A8.14 findings and S.12 checklist ¦ decides: Whether findings are accepted, fixed, or block release ¦ evidence: docs/sdlc/review/<PR>-security.md, <PR>-pii.md, <ID>-compliance.md ¦ if unanswered: Release blocked
stage | 0 Intake (A1) | reads: docs/sdlc/inputs/<ID>/ (what the user drops in: story.md, epic.md, screenshots/*.png, figma.md) ¦ writes: kanban.md Backlog row; route to A2 ¦ checkpoint: — ¦ kanban: Backlog
stage | 1 Understand (A2) | reads: docs/sdlc/inputs/<ID>/ ¦ writes: docs/sdlc/stories/<ID>/: manifest.md, features.md (epic), stories.md, acceptance-criteria.md, scope.md, screen-inventory.md (screenshot), ux-states.md, ux-spec.md, scope-check.md, ready-report.md ¦ checkpoint: CP-01 Ready ¦ kanban: Backlog → Ready
stage | 2 Plan: design (A3) | reads: docs/sdlc/stories/<ID>/, screenshots ¦ writes: docs/sdlc/design/<ID>/: ui-baseline.md or extracted-design.md, layout-plan.md, tokens.json, components.md, responsive.md, ui-checklist.md; draft frontend/src/theme/ ¦ checkpoint: CP-02 Design approval ¦ kanban: Ready → Design
stage | 2 Plan: architecture (A4) | reads: docs/sdlc/stories/<ID>/, docs/sdlc/design/<ID>/ ¦ writes: docs/sdlc/architecture/: adr/ADR-*.md, stack-analysis.md, architecture.md, data-model.md, api/openapi.yaml, navigation.md, repo-structure.md, design-doc-<ID>.md, tasks-<ID>.md ¦ checkpoint: CP-03 Architecture approval ¦ kanban: Design
stage | 3 Build: backend (A6) | reads: tasks-<ID>.md, openapi.yaml, data-model.md ¦ writes: backend/ (migrations, api, validation, seed/synthetic, config, Dockerfile); docs/sdlc/build/plans, task-gate, pr files; docs/sdlc/tests/contract-<run>.md ¦ checkpoint: — ¦ kanban: Design → In Progress
stage | 3 Build: frontend (A5) | reads: tasks-<ID>.md, design/<ID>/, navigation.md, openapi.yaml, seed data ¦ writes: frontend/ (components, screens, state, routes, api, theme); docs/sdlc/build/plans, task-gate, pr files ¦ checkpoint: — ¦ kanban: In Progress
stage | 4 Verify: tests (A7) | reads: stories/<ID>/, PR branch, openapi.yaml ¦ writes: tests/, frontend/tests/, backend/tests/; docs/sdlc/tests/: test-plan, traceability, results, defects, quality-summary ¦ checkpoint: CP-04 Quality GO ¦ kanban: In Progress → Testing
stage | 4 Verify: review (A8) | reads: PR diff, CI results, ADRs, tokens.json ¦ writes: docs/sdlc/review/<PR>-*.md (review, summary, checklist, secrets, design, loops) ¦ checkpoint: CP-06 if loop limit ¦ kanban: Testing → Review
stage | 5 Release (A8) | reads: quality-summary (GO), review files, CHANGELOG ¦ writes: CHANGELOG.md, .github/workflows/ci.yml and deploy.yml, deploy/, docs/sdlc/release/checklist-<version>.md ¦ checkpoint: CP-05 Release approval ¦ kanban: Review → Release Ready → Done
rule | R1 Traceability | Every output item cites its source: input ID, file, line, screenshot region or Figma node.
rule | R2 No invented values | A value the source does not give is written TBD and raised as a CP-07 checkpoint. Never guessed.
rule | R3 Humans decide | Agents propose options. A named person records each decision with a date in the checkpoint file.
rule | R4 Fresh-context verification | Before every handoff, S.04 runs in a new chat and compares output with input.
rule | R5 Checkpoints are human | No agent sets a checkpoint to APPROVED. A1 writes OPEN and blocks the item until a human answers.
rule | R6 Loop limit | Fix loops stop at the limit in config.yml (PROPOSED 3) and raise CP-06.
rule | R7 Tool over opinion | Lint, tests, scans and linters decide. Their output is attached to the handoff.
rule | R8 Visible uncertainty | Every output file ends with a 'Checkpoints raised' section, even if empty.
rule | R9 Separation of duties | The agent that reviews a change does not approve its release; a developer does not merge its own PR.
rule | R10 Labeled proposals | A default chosen by an agent is marked PROPOSED with a reason until a checkpoint approves it.
rule | R11 Token-optimized development | A skill reads only the files named in its INPUT, never a whole folder. It writes only the template fields, cites files by path instead of pasting them, and keeps each output under the length set in config.yml. Shared skills load only when called. One stage per chat; verification runs in a fresh chat with only the input and output files.